## Sheet1
Title : AUTONOMOUS EMERGENCY BRAKING SYSTEM
Harinivash K, Mohamed Asharaf M, Giriprasath M U, Sivaranjani P, Shivani B
DATE | FROM | TO | ATTENDEES | SCRIBE | POINTS DISCUSSED | ACTION
WEEK - 01
26.04.2023 | 9:45 | 10:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | We have discussed the overall idea of an Autonomous Emergency Braking (AEB) system, including the necessary test cases, specifications, and inputs and outputs for the system. We also analyzed the frontend technology, such as sensors, cameras, radar, and lidar. When discussing AEB with colleagues, it is important to emphasize the benefits of the technology and how it can improve road safety. Additionally, we have discussed about the various types of AEB systems, including those that only detect other vehicles and those that can also detect pedestrians.We have referred many youtube videos and understood how the AEB system works. | we are separating work from the project. shivani and ashraf doing presentation work and others are looking into the autonomous emergency braking system.
27.04.2023 | 10:00 | 11:15 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | We had discussed about the working of autonomous emergency braking system and details of functional requirements.The specific requirements for AEB systems can vary depending on the region, but here are some general requirements are Sensing Range,Detection Accuracy,Collision Avoidance,Warning System,False Alarm Rate and Testing Standards these are all terms are important points. some of the testcase standards of the AEB system and calculation part of the AEB system these are all things we had discussed Today. We have gathered some formulas required for the AEB system and started analysing the functional requirements | shivani doing presentation work and others are detail studying about the calculation part of the autonomous emergency braking systems and learning the working of model.
28.04.2023 | 9:45 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | In today's meeting, the functional requirements of the autonomous emergency braking system has been discussed.what are all the parameters are given,input and output of the autonomous emergency braking system.We have to find the caluculation of an AEB system typically involves several steps.The main steps are object detection uses sensors to detect the objects infront of the vehicle,Risk assessment are analyzes the object trajectory and determines whether there is a risk of collision,brake application decides to activate the brakes,it sends a signal to the vehicle braking system to apply the brakes and collision avoidance is successful in applying the brakes in time,it can prevent or reduce the severity of a collision.The accuracy and effectiveness of the system depend on the quality of the sensors and the system's programming. By calculating relative velocity, Time to collision , deceleration and breaking pressure We have checked whether mathematical output is correct. | calculation has to be done for the autonomous emergency braking system.Need to integrate the input,ouput and parameters in the rough model. To analyse the Functional requirements. To find how the basic matlab simulink model is to be created, like radar sensor , calculation blocks and analyse the existing vehicles AEB system parameters.
02.05.23 | 9:45 | 10:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | We had discussed about the preparation for presentation , made changes to the ppt slides and started idenfying the inputs and outputs by block diagram.discussed the contents indivudualy , analysed the working by seeing through the reserch papers related to AEB . Came through the flow of identifying the TTC and decelaration . After presentation , we had splitted the work to identify the values and range for all the formulas . | Harinivash , ashraf and giriprasath will be identifying the process and how to set the threshold limit to the TTC value .break control and pressure calculation of break pedal to be calculated
03.05.23 | 10:00 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | We had searched through the browser about the flow of AEB and found out the approximate value of TTC and deceleration , but the results were not sure whether its correct or not , after the discussion call , we had clarity about the derivation of deceleration and the function of giving partial breaking and full breaking . break pedal pressure given by the driver must be calculated to execute partial breaking and full breaking . | Giriprasath assigned to findout how much pressure needed to be given by the driver after warning phase . Others had seen the range and calculation with our own values of speed and distance
04.05.23 | 9:45 | 10:40 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | After seeing through the contents related to AEB , we had started to create flow chart and started final calculation for strategy document . Shivani and sivaranjini discussed about the test plan document and what will be the possible test cases for each phases and sub test cases for every parameter range . after discussion call , we had got some more time to determine the calculation of pressure in both partial breaking and full breaking phase . | Want to crosscheck , whether the calculation done is correct or not with respective how much pressure to be given , when the pressure given by the driver is not sufficient . Want to determine the time interval for each phase and how much time will take to complete , partial breaking and full breaking
WEEK - 02
05.05.23 | 10:00 | 11:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | we have done a model calculation but the output of the braking force is insufficient while calculating . we have discussed about the time frame how to divide the time for warning , partial braking and full braking. we have calculate the speed and deceleration after certain time and divided the time for two equal half but if we add the output distance is higher than the stopping distance so we have notice than we have made a mistake somewhere so we have to redo the entire calculation . We have discussed about the strategy document | want to redo all the calculation and ensure it is correct ,need to correct the flow chart and analyse the inputs and outputs , to find the threshold values for comparing the ttc , need to decide the time frame for each phase
08.05.23 | 10:00 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | Discussed about the functional requirements and changed the flow diagram . Analysed what are all the errors occur in the autonomous emergency braking system . Included some calculation in the stratergy document . preparing for the presentation for the functional requirement approval . Discussed about how to start the model and how to implement it . | Assigning works for individuals ashraf and giri prasath for matlab model . Shivani Harinivash and sivaranjani for preparing test documents and writing test cases
09.05.23 | 9.45 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | Started matlab model and discussed about what are indications or warning should be shown in the emergency braking system . discussed about different testings like unit testing , isolation testing . started doing test stratergy document and decided what are the testing we are conducting in out model , what are the steps to conduct unit testing . Discussed about modeling drivers pedal pressure input in matlab and the calculation blocks . | Ashraf and giriprasath doing matlab model and to create pedal pressure input system within tomorrow . shivani harinivash and sivaranjani doing test plan document
10.05.23 | 10:00 | 11:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | There is little complication in using the constant block input in other subsystems by using goto and from block . discussed about the ttcmin and ttcemerg and how to split the timing for the braking system. included collision warning , partial brake warning , full brake warning and discussed about the test plan document what are the contents and tables should be included in the test plan document | Writing test cases . To complete the test plan document cover page, document history . To get the output for single cycle.
11.05.23 | 10:15 | 11:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | Analysed about the diagnostics related errors and discussed how to indicate the errors like brake pedal sensor failure , Brake malfunctioning . Discussed about the single iteration failure and analysed what are the mistakes done in the matlab model and correcting some errors in the AEB system | To update the test cases and to start the test result document , Try to complete the matlab model for single cycle output . check the inputs and outputs are aligned and the process are in the subsystem . update some formulas in the model . Try to make it as a closed loop system
12.05.23 | 11:00 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Harinivash | We are at the final stage of our matlab model to complete the requirements and start testing the AEB model. In our model we have included the diagnostics error that needs to be addressed in the model so if there is any errors identified and indicated through fault end warning also we can directly list what are the possible error that could occur over a period of time. blocks club together and arranged with according to the colour code for input and output which makes easier to identify. we are ready with our document . but still trying to make it as a closed loop system but it is difficult for us to implement so we are discussing about that and how to implement in the aeb system . | To complete the final test cases, test result template should be completed and we have to edit the simulink model according to the input , output and warning system . need to rename the blocks correctly , need to mention the signal names and finally after completing the model the test result doc should be updated and enter the data in the required table
WEEK - 03
15.05.23 | 10:00 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Shivani | We have discussed about how to generate a report in matlab . We have referred and tried to generate a report but we have faced some errors in generating . We have discussed about the test cases and added some test cases in the document. Then we have discussed about the template of the model like adding the areas for input and output , giving correct naming for all the blocks and signal lines. | Giri prasath and ashraf doing the matlab model . shivani , sivaranjani and harinivash adding the test cases
16.05.23 | 11:30 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Shivani | During the discussion, we identified certain conditions that were absent in the MATLAB model. To address this, we explored various approaches to implement the missing conditions and incorporate the necessary subsystem calculations within the existing model. We discussed potential strategies such as introducing conditional statements or logical operators to check and handle the required conditions. | Need to find how to generate a report in matlab by referring videos , Update all the test documents, parallelly the matlab model works are to be complete.
17.05.23 | 11:20 | 12:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Shivani | During the discussion, we made modifications to certain values for the input parameters in the test case. the test result file was updated accordingly to reflect these changes. In our team discussion, we planned about preparation process for the final review of the project. We reviewed the project's overall progress and ensuring that all the necessary tasks were completed satisfactorily. We discussed the key points and challenges faced throughout the project, aiming to present a good final review. | Ensuring the matlab model is completed , To link all the subsystems and verify the output
18.05.23 | 11:45 | 1:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Shivani | In our discussion, we talked about the important information and details related to each separate subsystem of the model. We focused on understanding how each subsystem works and discussed its role in the overall system. To present this information in a PowerPoint presentation, we decided to create a step-by-step workflow for each subsystem. This workflow will visually show the sequence of actions and interactions within each subsystem, helping the audience understand its functioning clearly. | The test cases are to be tested in the model and update the result document
19.05.23 | 11:00 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Shivani | After conducting further research, the team referred with reference papers to increase our understanding of the AEB (Autonomous Emergency Braking) system. A meeting was held among the team members to discuss the model and evaluate its feasibility. During the meeting, Ashraf and Giriprasath provided an in-depth explanation of the AEB model with its key components and functionality. They actively addressed the team's doubts and concerns, ensuring a clear understanding of the model. | To prepare PPT for final review and to complete the report works
WEEK - 04
22.05.23 | 10:00 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | Last week ,we had discussed about how to generate a report in matlab and also we explored various necessary subsystem calculations within the existing model. Now we have completed the report generation in matlab and added some test cases in the document.We have to clear the modifications to certain values for the input parameters in the test case.Now we all cleared the autonomous emergency braking system model(AEB). | update all the report model and complete the autonomous emergency braking system model(AEB).
23.05.23 | 11:30 | 12:30 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | During today's meeting, we extensively covered the requirements for creating the final presentation on the Autonomous Emergency Braking System (AEB). We dedicated significant time to discussing and providing detailed information on the content that should be included in the presentation | Need to finish the final presentation PPT and understand the document of AEB.
24.05.23 | 10:30 | 11:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | In Today's MoM,We had an overview on the created presentation,the contents are splitted individually some of the main contents are functions of each subsystem, Brake pedal force calculation,comparing both decceleration,conditions for full braking, partial brake and braking force calculations,speed compariosn and output for display these are all the main stuffs are added in the final review Presentation.Corrections and other discussions to present the presentation was discussed. | Make all the corrections noted in the final presentation of Autonomous Emergency Braking system.
25.05.03 | 11:15 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | We have discussed what are the deliverables to be submitted and to check all the documents are completed. We have decided to add functional requirements and future scope in our final ppt . Faced some errors while generating model adivsor report so we have corrected the errors. | To add some model descriptions and to review the test documents are correct . Try to generate test harness report
26.05.23 | 11:15 | 12:00 | Harinivash K Mohamed Asharaf M Giriprasath M U Sivaranjani P Shivani B | Sivaranjani | Today's meeting ,We had discussing about the task of developing a PowerPoint presentation focused on Powerstrain. We began by encouraging each individual to contribute their ideas and suggestions regarding the content that should be incorporated into the presentation. Following this collaborative brainstorming session, we proceeded to commence the actual creation of the presentation, leveraging the shared insights and information provided by the team members. | To complete and send the deliverables and prepare for final review